## Sprint 1
Rent-a-Car - Sprint 1
Sprint Dates: 5/29 - 6/9, 2017
|  |  |  | Available working hours in the sprint |  |  |  | Days in sprint: 9.5
Sprint Goal |  |  |  |  | M | Tu | W | Th | F | M | Tu | W | Th | F | Total
|  |  |  | Developers | Sprint Planning | Sprint Planning | Sprint Planning | Design | Design | Design | Design | Coding | Coding | Sprint Review
|  |  |  | Matheus Gonclaves | 1 | 2 | 0 | 2 | 0 | 2 | 3 | 2 | 4 | 2
|  |  |  | Brandon Gray | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 14 | 2
James Jeffery
|  |  |  | Tony Jimogaon | 1 | 0 | 1 | 1 | 2 | 1 | 1 | 6 | 2
Total sprint hours:
Total per day:
[Burndown chart goes here and shows hours and story points]
Feature Burndown - Based on estimated hours remaining
ID | Task | Description | Acceptance Criteria | Type | Story Points | Responsible | M | Tu | W | Th | F | M | Tu | W | Th | F | Done (Y) | Accepted (Y/N)
23 | Add a car's brand, model, color, year, availability, and daily price | As a car inventory system, I want to record a car's information so that customers and the store are aware. | When I add a car to the inventory, all its information is recorded. | Feature | 2 | (name) | M: (planned hours | Y | Y
| Initialize the car's brand | Give the car's brand a value and store it |  | Requirement |  |  | M: for each day
| Initialize the car's model | Give the car's model a value and store it |  | Requirement |  |  | M: and task)
| Initialize the car's color | Give the car's color a value and store it |  | Requirement
| Initialize the car's year | Give the car's year a value and store it |  | Requirement
| Initialize the car's availability | Give the car's availability a value and store it |  | Requirement
| Initialize the car's daily price | Give the car's daily price a value and store it |  | Requirement
21 | Enter a customer's first and last name, age, phone number, and email | As a store clerk, I want to record a customer's information so that the customer can rent and return a car. | When I enter the customer's information, the car should be rented. | Feature | 2 | (name) | [10 empty] | Y | Y
| Allow input for the customer's first name | Input the customer's first name |  | Requirement
| Allow input for the customer's last name | Input the customer's last name |  | Requirement
| Allow input for the customer's age | Input or choose the customer's age |  | Requirement
| Allow input for the customer's phone number | Input the customer's phone number |  | Requirement
| Allow input for the customer's email address | Input the customer's email address |  | Requirement
22 | Get customer's first name and last name, age, phone number, and email | As a customer storage system, I want to receive a customer's information so that the car may be rented. | When the customer's information is received, the car will be rented. | Feature | 2 | (name) | [10 empty] | Y | Y
| Record the customer's first name | Store the customer's first name |  | Requirement
| Record the customer's last name | Store the customer's last name |  | Requirement
| Record the customer's age | Store the customer's age |  | Requirement
| Record the customer's phone number | Store the customer's phone number |  | Requirement
| Record the customer's email address | Store the customer's email address |  | Requirement
Actual Hrs Remaining
Schedule Hrs Remaining
Story Points Remaining | [6 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Issues
Matheus Gonclaves
Brandon Gray
James Jeffery
Tony Jimogaon
Demonstrate the ability to keep track of customers and cars and register cars to customers.