## Sprint 1
Rent-a-Car - Sprint 1 Backlog
Sprint Dates: 5/29 - 6/9, 2017
|  |  | Available working hours in the sprint |  |  |  | Days in sprint: 9.5
Sprint Goal |  |  |  | M | Tu | W | Th | F | M | Tu | W | Th | F | Total
|  |  | Developers | Sprint Planning | Sprint Planning | Sprint Planning | Design | Design | Design | Design | Coding | Coding | Sprint Review
|  |  | Matheus Gonclaves | 1 | 2 | 0 | 2 | 0 | 2 | 3 | 2 | 4 | 2 | 18
|  |  | Brandon Gray | 2 | 3 | 3 | 4 | 4 | 4 | 14 | 0 | 0 | 7 | 41
|  |  | James Jeffrey | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 6 | 6 | 1 | 23
|  |  | Tony Jimogaon | 1 | 0 | 2 | 1 | 2 | 2 | 1 | 6 | 3 | 2 | 20
|  |  |  | Days in sprint: 9.5 F: Total sprint hours: | 102
|  |  |  | Days in sprint: 9.5 F: Total per day: | 16
Feature Burndown - Based on estimated hours remaining
ID | Task | Description | Acceptance Criteria | Type | Story Points | Responsible | M | Tu | W | Th | F | M | Tu | W | Th | F | Done (Y) | Accepted (Y/N)
23 | Add a car's brand, model, color, year, availability, and daily price | As a car inventory system, I want to record a car's information so that customers and the store are aware. | When I add a car to the inventory, all its information is recorded. | Feature | 2 | James Jeffrey | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | Y | Y
| Initialize the car's brand | Give the car's brand a value and store it | When I add a car to the inventory, its brand is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.3 | 0.5 | 0
| Initialize the car's model | Give the car's model a value and store it | When I add a car to the inventory, its model is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.5 | 0.2 | 0
| Initialize the car's color | Give the car's color a value and store it | When I add a car to the inventory, its color is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.1 | 0.5 | 0
| Initialize the car's year | Give the car's year a value and store it | When I add a car to the inventory, its year is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.3 | 0
| Initialize the car's availability | Give the car's availability a value and store it | When I add a car to the inventory, its availability is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0
| Initialize the car's daily price | Give the car's daily price a value and store it | When I add a car to the inventory, its daily price is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.5 | 0
21 | Enter a customer's first and last name, age, phone number, and email | As a store clerk, I want to record a customer's information so that the customer can rent and return a car. | When I enter the customer's information, the car should be rented. | Feature | 2 | James Jeffrey | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | Y | Y
| Allow input for the customer's first name | Input the customer's first name | When I enter the customer's information, the first name is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.5 | 0.5 | 0
| Allow input for the customer's last name | Input the customer's last name | When I enter the customer's information, the last name is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.2 | 0.5 | 0
| Allow input for the customer's age | Input or choose the customer's age | When I enter for the information, for customer's age is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0
| Allow input for the customer's phone number | Input the customer's phone number | When I enter the customer's information, the phone number is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.3 | 1 | 0
| Allow input for the customer's email address | Input the customer's email address | When I enter the customer's information, the email address is recorded. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0
22 | Get customer's first name and last name, age, phone number, and email | As a customer storage system, I want to receive a customer's information so that the car may be rented. | When the customer's information is received, the car will be rented. | Feature | 2 | Tony Jimogaon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Y | Y
| Record the customer's first name | Store the customer's first name | When the customer's information is received, store their first name. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Record the customer's last name | Store the customer's last name | When the customer's information is received, store their last name. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Record the customer's age | Store the customer's age | When the the information is received, store their customer's age. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0
| Record the customer's phone number | Store the customer's phone number | When the customer's information is received, store their phone number. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Record the customer's email address | Store the customer's email address | When the customer's information is received, store their email address. | Requirement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0
Actual Hrs Remaining | [6 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Schedule Hrs Remaining | [6 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 0 | 0
Story Points Remaining | [6 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Issues | [6 empty] | 14 | 12.5 | 11 | 9.5 | 8 | 6.5 | 5 | 3.5 | 2 | 0
Matheus Gonclaves
Brandon Gray
James Jeffrey
Tony Jimogaon
Demonstrate the ability to keep track of customers and cars and register cars to customers.