## Sprint 1
Rent-a-Car - Sprint 1
Sprint Dates: 5/29 - 6/9, 2017
|  |  |  | Available working hours in the sprint |  |  |  | Days in sprint: 9.5
Sprint Goal |  |  |  |  | M | Tu | W | Th | F | M | T | W | T | F | Total
|  |  |  | Developers | Sprint Planning | Sprint Planning | Sprint Planning | Design | Design | Design | Design | Coding | Coding | Sprint Review
Matheus Gonclaves
|  |  |  | Brandon Gray | 2 | 2 | 3 | 3 | 4 | 4 | 4
James Jeffery
|  |  |  | Tony Jimogaon | 1 | 0 | 1 | 1 | 2 | 1 | 1 | 6 | 2
Total sprint hours:
Total per day:
[Burndown chart goes here and shows hours and story points]
Feature Burndown - Based on estimated hours remaining
ID | Task | Description | Acceptance Criteria | Type | Story Points | Responsible | M | Tu | W | Th | F | M | Tu | W | Th | F | Done (Y) | Accepted (Y/N)
21 | Add a car's brand, model, color, year, availability, and daily price | As a car inventory system, I want to record a car's information so that customers and the store are aware. | When I add a car to the inventory, all its information is recorded. | Feature | (expected detail) | (name) | M: (planned hours |  | N
| Initialize the car's brand | Give the car's brand a value and store it |  | Requirement |  |  | M: for each day
| Initialize the car's model | Give the car's model a value and store it |  | Requirement |  |  | M: and task)
| Initialize the car's color | Give the car's color a value and store it |  | Requirement
| Initialize the car's year | Give the car's year a value and store it |  | Requirement
| Initialize the car's availability | Give the car's availability a value and store it |  | Requirement
| Initialize the car's daily price | Give the car's daily price a value and store it |  | Requirement
19 | Enter a customer's first and last name, age, phone number, and email | As a store clerk, I want to record a customer's information so that the customer can rent and return a car. | When I enter the customer's information, the car should be rented. | Feature | (any scale) | (name) | [11 empty] | N
| Allow input for the customer's first name | Input the customer's first name |  | Requirement
| Allow input for the customer's last name | Input the customer's last name |  | Requirement
| Allow input for the customer's age | Input or choose the customer's age |  | Requirement
| Allow input for the customer's phone number | Input the customer's phone number |  | Requirement
| Allow input for the customer's email address | Input the customer's email address |  | Requirement
20 | Get a customer's first and last name, age, phone number, and email | As a customer storage system, I want to receive a customer's information so that car may be rented. | When the customer's information is received, the car will be rented. | Feature |  | (name) | [11 empty] | N
| Record the customer's first name | Store the customer's first name |  | Requirement
| Record the customer's last name | Store the customer's last name |  | Requirement
| Record the customer's age | Store the customer's age |  | Requirement
| Record the customer's phone number | Store the customer's phone number |  | Requirement
| Record the customer's email address | Store the customer's email address |  | Requirement
Actual Hrs Remaining
Schedule Hrs Remaining
Story Points Remaining
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Issues
Matheus Gonclaves
(issue)
(issue)
(…)
Brandon Gray
(issue)
(issue)
(…)
James Jeffery
(issue)
(issue)
(…)
Tony Jimogaon
(issue)
(issue)
(…)
Demonstrate the ability to keep track of customers and cars and register cars to customers.